## labour
CONSTRUCTION MANAGEMENT INSTITUTE (CMI) WITH BAHIR DAR INSTITUTE OF TECHNOLOGY (BiT)
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADES
Labour Productivity Data Records
Form 2
[10 empty] | Work Time |  |  | Total Manhours (6x8) (9) | Unit (10) | Daily Units Completed (11) | Productivity | Problem Code (13)
Data Count: | Date | Proect Code | Data Collector | Number of crews: | Task Type (1) | Particulars / description (2) | Location (3) | Crew Size (4) | Crew Composition (Foreman, Worker, Helper, etc.) (5) | Work Time - R (6) | Work Time - OT (7) | Total (6+7) (8) |  |  |  | Installed Quantity / T. Manhours (9/11) (12)
1 | 2017-04-02 | 02 | Kidist Bedada | 2 | 08-lining | Canal wall and bed concrete work by using stationary mixer with labor |  | 11 | 2F; 10W | 8 | 0 | 8 |  | m3 | 35.043 |  | 1E, 1D
2 | 2017-04-02 | 2 | Kidist Bedada | 2 | 08-lining | Canal wall and bed concrete work by using stationary mixer with labor |  | 11 | 2F; 10W | 8 | 0 | 8 |  | m3 | 35.043 |  | 1E, 1D

## work_sampling
Bahir Dar University
Bahir Dar Institute of Technology, BiT
|  | Project: |  | Study on Productivity Norm of Building Construction Trades around Bahir Dar City
|  | Consultant: |  | Faculty of Civil and Water Resource Engineering
|  | Lead Consultant: |  | Addis Ababa Institute of Technology, AAIT
|  | Client: |  | FDRE Construction Management Institute (CMI)
|  | Title of form: |  | Work Sampling
Data Collection Form Description |  | Observation Time (Hr.) |  | 49:59
Data count: | 02/ 03/2017 E.C | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Project Code: |  | Observation Time: (min)
Crew tag: |  | CREW 1 | Direct
Location: Ground |  |  | Preparatory work
Tools and equipment
Task type code: |  |  | Material handling
Waiting
Travel
Personal
Sum
Data Collector |  | Observation Time (Hr.) |  | 49:59 1: 3:00:00 ጥዋት - 4:00
|  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Observation Time: (min)
|  | CREW 1 | Direct
Preparatory work
Tools and equipment
Material handling
Waiting
Travel
Personal
Sum
|  | Observation Time (Hr.) |  | 3:00:00 ጥዋት - 4:00 1: 51:59
|  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Observation Time: (min)
|  | CREW 1 | Direct
Preparatory work
Tools and equipment
Material handling
Waiting
Travel
Personal
Sum
|  | Observation Time (Hr.) |  | 51:59 1: 52:59
|  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Observation Time: (min)
|  | CREW 1 | Direct
Preparatory work
Tools and equipment
Material handling
Waiting
Travel
Personal
Sum
|  | Observation Time (Hr.) |  | 52:59 1: 66:59
|  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Observation Time: (min)
|  | CREW 1 | Direct
Preparatory work
Tools and equipment
Material handling
Waiting
Travel
Personal
Sum
|  | Observation Time (Hr.) |  | 66:59 1: 67:59
|  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Observation Time: (min)
|  | CREW 1 | Direct
Preparatory work
Tools and equipment
Material handling
Waiting
Travel
Personal
Sum
|  | Observation Time (Hr.) |  | 67:59 1: 68:59
|  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Observation Time: (min)
|  | CREW 1 | Direct
Preparatory work
Tools and equipment
Material handling
Waiting
Travel
Personal
Sum
|  | Observation Time (Hr.) |  | 68:59 1: 69:59
|  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Observation Time: (min)
|  | CREW 1 | Direct
Preparatory work
Tools and equipment
Material handling
Waiting
Travel
Personal
Sum

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE |  |  |  |  | Project Code
Form -6 - Daily Input Variables |  |  |  |  | Task/particular
Data Collector
[5 empty] | Data count | 1 | 2 | 3 | 5
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description | Value
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | Range (1 - 20) | Vaules for each of the crews understudy | 4
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | Range og each category (0 - 10) | Vaules for each of the crews understudy | 1 F, 2L, 1H
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | Range (0 -38) | Over all project activities (besides the one under study).