## labour
CONSTRUCTION MANAGEMENT INSTITUTE (CMI) WITH BAHIR DAR INSTITUTE OF TECHNOLOGY (BiT)
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADES
Labour Productivity Data Records
Form 2
[10 empty] | Work Time |  |  | Total Manhours (6x8) (9) | Unit (10) | Daily Units Completed (11) | Productivity | Problem Code (13)
Data Count: | Date | Proect Code | Data Collector | Number of crews: | Task Type (1) | Particulars / description (2) | Location (3) | Crew Size (4) | Crew Composition (Foreman, Worker, Helper, etc.) (5) | Work Time - R (6) | Work Time - OT (7) | Total (6+7) (8) |  |  |  | Installed Quantity / T. Manhours (9/11) (12)
31 | 2017-05-05 | 2 | Gedefaw Dessie | 1 | form eork | water supply system ,division 13, form work, for wall of reservoir , work by labou |  | 7 | 1 foreman, 6 worker | 7:00 | 0 | 7:00 | 49:00 | m2 | 21 | 0.43 | 2j
[12 empty] | 0 | 0 |  |  | #DIV/0! | 7a
[12 empty] | 0 | 0 |  |  | #DIV/0!
[12 empty] | 0 | 0 |  |  | #DIV/0!
[12 empty] | 0 | 0 |  |  | #DIV/0!

## work_sampling
Bahir Dar University
Bahir Dar Institute of Technology, BiT
|  |  | Project: |  | Study on Productivity Norm of Water Construction Trades
|  |  | Consultant: |  | Faculty of Civil and Water Resource Engineering
|  |  | Lead Consultant: |  | Addis Ababa Institute of Technology, AAIT
|  |  | Client: |  | FDRE Construction Management Institute (CMI)
|  |  | Title of form: |  | Work Sampling
Data Collection Form Description |  |  | Observation Time (Hr.) |  | 2:00:00 ጥዋት - 3:00 ጥዋት | [17 empty] | 3:00:00 ጥዋት - 4:00 ጥዋት
Data count: | 31 | 05/ 05/2017 E.C | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Project Code: | 2 |  | Observation Time: (min) |  | 2 | 6 | 10 | 13 | 16 | 19 | 22 | 25 | 28 | 31 | 34 | 37 | 40 | 43 | 46 | 49 | 53 | 56 | 59 | 2 | 5 | 8 | 12 | 15 | 18 | 22 | 25 | 29 | 32 | 36 | 39 | 42 | 45 | 48 | 52 | 55
Crew tag: |  |  | CREW 1 | Direct | 3 | 4 | 4 | 3 | 6 | 6 | 4 | 5 | 7 | 5 | 6 | 6 | 5 | 4 | 7 | 6 | 4 | 5 | 5 | 6 |  | 3 | 6 | 4 | 5 | 3 | 6 | 5 | 4 | 5 | 5 | 2 | 5 | 6 | 7 | 6
Location: | Ground |  |  | Preparatory work | 2:00:00 ጥዋት - 3:00 ጥዋት 17 53: 2; 3:00:00 ጥዋት - 4:00 ጥዋት 3 5: 4; 3:00:00 ጥዋት - 4:00 ጥዋት 10 29: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 14 42: 3
|  |  |  | Tools and equipment | 2:00:00 ጥዋት - 3:00 ጥዋት 3 10: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 11 32: 2; 3:00:00 ጥዋት - 4:00 ጥዋት 13 39: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 18 55: 1
Task type code: | form work |  |  | Material handling | 2:00:00 ጥዋት - 3:00 ጥዋት 1 2: 2; 2:00:00 ጥዋት - 3:00 ጥዋት 2 6: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 4 13: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 6 19: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 8 25: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 11 34: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 13 40: 2; 2:00:00 ጥዋት - 3:00 ጥዋት 16 49: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 18 56: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 1 59: 2; 3:00:00 ጥዋት - 4:00 ጥዋት 4 8: 3; 3:00:00 ጥዋት - 4:00 ጥዋት 6 15: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 7 18: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 8 22: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 13 39: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 16 48: 1
|  |  |  | Waiting | 2 | 1 | 2 | 2 | 1 |  | 3 | 1 |  | 2 |  | 1 |  | 3 |  |  | 1 |  |  | 1 | 2 |  | 1 |  | 1 | 3 | 1 | 1 | 1 | 2 |  | 1 | 2
|  |  |  | Travel | 2:00:00 ጥዋት - 3:00 ጥዋት 2 6: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 4 13: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 18 56: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 3 5: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 4 8: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 6 15: 2; 3:00:00 ጥዋት - 4:00 ጥዋት 14 42: 1
Personal
|  |  |  | Sum | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
Data Collector | Gedefaw | Dessie | Observation Time (Hr.) |  | 2:00:00 ጥዋት - 3:00 ጥዋት 1 2: 4:00:00 ጥዋት - 5:00 ጥዋት; 3:00:00 ጥዋት - 4:00 ጥዋት 1 59: 5:00:00 ጥዋት - 6:00 ጥዋት
|  |  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  |  | Observation Time: (min) |  | 58 | 2 | 6 | 10 | 13 | 17 | 20 | 23 | 26 | 29 | 33 | 36 | 39 | 42 | 45 | 48 | 52 | 55 | 58 | 2 | 6 | 9 | 12 | 15 | 18 | 22 | 25 | 29 | 32 | 35 | 38 | 41 | 44 | 48 | 50 | 53
|  |  | CREW 1 | Direct | 4 | 5 | 4 | 3 | 5 | 5 | 4 | 5 | 6 | 4 | 3 | 5 | 3 | 6 | 6 | 4 | 5 | 4 | 4 | 3 | 5 | 6 | 5 | 7 | 7 |  | 2 | 5 | 3 | 4 | 4 | 3 | 5 | 5 | 7 | 6
|  |  |  | Preparatory work | 4:00:00 ጥዋት - 5:00 ጥዋት 4: 3; 5:00:00 ጥዋት - 6:00 ጥዋት 8: 4
|  |  |  | Tools and equipment | 4:00:00 ጥዋት - 5:00 ጥዋት 7: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 9: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 10: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 13: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 12: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 14: 2
|  |  |  | Material handling | 4:00:00 ጥዋት - 5:00 ጥዋት 3: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 11: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 12: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 14: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 18: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 1: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 2: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 8: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 9: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 10: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 11: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 13: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 14: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 15: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 16: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 18: 1
|  |  |  | Waiting | 4:00:00 ጥዋት - 5:00 ጥዋት 1: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 2: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 5: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 6: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 7: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 8: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 10: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 11: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 12: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 16: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 17: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 2: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 3: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 4: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 5: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 9: 3; 5:00:00 ጥዋት - 6:00 ጥዋት 11: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 12: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 13: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 14: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 15: 1
|  |  |  | Travel | 4:00:00 ጥዋት - 5:00 ጥዋት 1: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 3: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 4: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 6: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 7: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 11: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 15: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 16: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 18: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 1: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 2: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 9: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 10: 1
|  |  |  | Personal | 4:00:00 ጥዋት - 5:00 ጥዋት 3: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 13: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 5: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 8: 1
|  |  |  | Sum | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  |  | Observation Time (Hr.) |  | 4:00:00 ጥዋት - 5:00 ጥዋት 1: 7:00:00 - 8:00 ከሰዓት; 5:00:00 ጥዋት - 6:00 ጥዋት 1: 7:52:00 - 8:50 ከሰዓት
|  |  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  |  | Observation Time: (min) |  | 56 | 0 | 4 | 6 | 9 | 12 | 15 | 18 | 22 | 26 | 29 | 32 | 35 | 39 | 42 | 45 | 48 | 52 | 54 | 57 | 0 | 3 | 6 | 9 | 12 | 15 | 20 | 23 | 26 | 29 | 32 | 35 | 38 | 42 | 45 | 48
|  |  | CREW 1 | Direct | 4 | 6 | 5 | 5 | 4 | 6 | 1 | 7 | 4 | 6 | 4 | 5 | 5 | 6 | 7 | 4 | 5 | 7 | 5 | 5 | 4 | 6 | 3 | 6 | 5 | 5 | 6 | 4 | 7 | 6 | 6 | 4 | 5 | 7 | 4 | 6
Preparatory work
|  |  |  | Tools and equipment | 7:00:00 - 8:00 ከሰዓት 1: 2; 7:00:00 - 8:00 ከሰዓት 4: 1; 7:00:00 - 8:00 ከሰዓት 11: 1; 7:00:00 - 8:00 ከሰዓት 16: 2; 7:52:00 - 8:50 ከሰዓት 3: 2; 7:52:00 - 8:50 ከሰዓት 5: 1; 7:52:00 - 8:50 ከሰዓት 8: 1; 7:52:00 - 8:50 ከሰዓት 14: 1
|  |  |  | Material handling | 7:00:00 - 8:00 ከሰዓት 5: 1; 7:00:00 - 8:00 ከሰዓት 7: 2; 7:00:00 - 8:00 ከሰዓት 9: 2; 7:00:00 - 8:00 ከሰዓት 10: 1; 7:00:00 - 8:00 ከሰዓት 12: 1; 7:00:00 - 8:00 ከሰዓት 14: 1; 7:52:00 - 8:50 ከሰዓት 2: 1; 7:52:00 - 8:50 ከሰዓት 9: 1; 7:52:00 - 8:50 ከሰዓት 10: 1; 7:52:00 - 8:50 ከሰዓት 13: 1; 7:52:00 - 8:50 ከሰዓት 15: 1; 7:52:00 - 8:50 ከሰዓት 17: 1; 7:52:00 - 8:50 ከሰዓት 18: 1
|  |  |  | Waiting | 1 | 1 |  | 1 | 2 | 1 | 1 |  | 1 |  | 2 | 1 | 2 |  |  |  | 2 |  | 2 | 1 | 1 | 1 | 3 | 1 |  | 1 |  | 1 |  | 1 |  | 2 | 1 |  | 2
|  |  |  | Travel | 7:00:00 - 8:00 ከሰዓት 3: 2; 7:00:00 - 8:00 ከሰዓት 7: 3; 7:00:00 - 8:00 ከሰዓት 16: 1; 7:52:00 - 8:50 ከሰዓት 7: 2; 7:52:00 - 8:50 ከሰዓት 10: 1
Personal
|  |  |  | Sum | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  |  | Observation Time (Hr.) |  | 7:00:00 - 8:00 ከሰዓት 1: 8:50:00 -9:50 ከሰዓት; 7:52:00 - 8:50 ከሰዓት 1: 9:50:00 -10:00 ከሰዓት
|  |  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  |  | Observation Time: (min) |  | 8:50:00 -9:50 ከሰዓት 1: 52; 8:50:00 -9:50 ከሰዓት 2: 56; 8:50:00 -9:50 ከሰዓት 3: 59; 8:50:00 -9:50 ከሰዓት 4: 3; 8:50:00 -9:50 ከሰዓት 5: 7; 8:50:00 -9:50 ከሰዓት 6: 10; 8:50:00 -9:50 ከሰዓት 7: 13; 8:50:00 -9:50 ከሰዓት 8: 17; 8:50:00 -9:50 ከሰዓት 9: 20; 8:50:00 -9:50 ከሰዓት 10: 23; 8:50:00 -9:50 ከሰዓት 11: 27; 8:50:00 -9:50 ከሰዓት 12: 30; 8:50:00 -9:50 ከሰዓት 13: 33; 8:50:00 -9:50 ከሰዓት 14: 27; 8:50:00 -9:50 ከሰዓት 15: 40; 8:50:00 -9:50 ከሰዓት 16: 43; 8:50:00 -9:50 ከሰዓት 17: 47; 8:50:00 -9:50 ከሰዓት 18: 50; 9:50:00 -10:00 ከሰዓት 1: 53; 9:50:00 -10:00 ከሰዓት 2: 57; 9:50:00 -10:00 ከሰዓት 3: 0
|  |  | CREW 1 | Direct | 8:50:00 -9:50 ከሰዓት 1: 3; 8:50:00 -9:50 ከሰዓት 2: 4; 8:50:00 -9:50 ከሰዓት 3: 3; 8:50:00 -9:50 ከሰዓት 4: 7; 8:50:00 -9:50 ከሰዓት 5: 6; 8:50:00 -9:50 ከሰዓት 6: 4; 8:50:00 -9:50 ከሰዓት 7: 3; 8:50:00 -9:50 ከሰዓት 8: 6; 8:50:00 -9:50 ከሰዓት 9: 4; 8:50:00 -9:50 ከሰዓት 10: 5; 8:50:00 -9:50 ከሰዓት 11: 5; 8:50:00 -9:50 ከሰዓት 12: 6; 8:50:00 -9:50 ከሰዓት 13: 3; 8:50:00 -9:50 ከሰዓት 14: 4; 8:50:00 -9:50 ከሰዓት 15: 6; 8:50:00 -9:50 ከሰዓት 16: 7; 8:50:00 -9:50 ከሰዓት 17: 6; 8:50:00 -9:50 ከሰዓት 18: 7; 9:50:00 -10:00 ከሰዓት 1: 4; 9:50:00 -10:00 ከሰዓት 2: 4; 9:50:00 -10:00 ከሰዓት 3: 2
|  |  |  | Preparatory work | 8:50:00 -9:50 ከሰዓት 3: 3
|  |  |  | Tools and equipment | 8:50:00 -9:50 ከሰዓት 1: 2; 8:50:00 -9:50 ከሰዓት 11: 1; 8:50:00 -9:50 ከሰዓት 13: 1
|  |  |  | Material handling | 8:50:00 -9:50 ከሰዓት 2: 1; 8:50:00 -9:50 ከሰዓት 6: 2; 8:50:00 -9:50 ከሰዓት 9: 1; 8:50:00 -9:50 ከሰዓት 12: 1; 9:50:00 -10:00 ከሰዓት 3: 1
|  |  |  | Waiting | 8:50:00 -9:50 ከሰዓት 1: 2; 8:50:00 -9:50 ከሰዓት 3: 1; 8:50:00 -9:50 ከሰዓት 5: 1; 8:50:00 -9:50 ከሰዓት 7: 2; 8:50:00 -9:50 ከሰዓት 9: 1; 8:50:00 -9:50 ከሰዓት 10: 2; 8:50:00 -9:50 ከሰዓት 11: 1; 8:50:00 -9:50 ከሰዓት 13: 3; 8:50:00 -9:50 ከሰዓት 14: 2; 8:50:00 -9:50 ከሰዓት 15: 1; 8:50:00 -9:50 ከሰዓት 17: 1; 9:50:00 -10:00 ከሰዓት 1: 3; 9:50:00 -10:00 ከሰዓት 2: 2; 9:50:00 -10:00 ከሰዓት 3: 2
|  |  |  | Travel | 8:50:00 -9:50 ከሰዓት 2: 2; 8:50:00 -9:50 ከሰዓት 6: 1; 8:50:00 -9:50 ከሰዓት 7: 2; 8:50:00 -9:50 ከሰዓት 9: 1; 8:50:00 -9:50 ከሰዓት 14: 1; 9:50:00 -10:00 ከሰዓት 2: 1; 9:50:00 -10:00 ከሰዓት 3: 2
Personal | bar: 8:50:00 -9:50 ከሰዓት 8
|  |  |  | Sum | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form -6 - Daily Input Variables
Project Code |  | 2 | Task/particular | form work
Data Collector |  | Gedefaw Dessie | Data Count | 31 |  | Date | 2017-05-05
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | observation | 7 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | observation | 1 foreman, 6 worker | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | observation | 1 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 4 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 4 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 5 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | interview | 3 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | interview | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | interview | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | interview | 6 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | interview | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | interview | 2 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | count | 2 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | p | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) |  |  | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) |  |  | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) |  |  | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) |  |  | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 40% | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).