## labour
CONSTRUCTION MANAGEMENT INSTITUTE (CMI) WITH BAHIR DAR INSTITUTE OF TECHNOLOGY (BiT)
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADES
Labour Productivity Data Records
Form 2
[10 empty] | Work Time |  |  | Total Manhours (6x8) (9) | Unit (10) | Daily Units Completed (11) | Productivity | Problem Code (13)
Data Count: | Date | Proect Code | Data Collector | Number of crews: | Task Type (1) | Particulars / description (2) | Location (3) | Crew Size (4) | Crew Composition (Foreman, Worker, Helper, etc.) (5) | Work Time - R (6) | Work Time - OT (7) | Total (6+7) (8) |  |  |  | Installed Quantity / T. Manhours (9/11) (12)
35 | 2017-05-09 | 2 | Gedefaw Dessie | 1 | excavation | water supply ,division 13,excavation sand soil 30cm depth by labour work |  | 6 | 1 foreman , 5 worker | 7:30 | 0:00 | 7:30 | 45:00 | m3 | 3.5 | 0.08m3/hr | 1c
[12 empty] | 0 | 0 |  |  |  | 3a
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0

## work_sampling
Bahir Dar University
Bahir Dar Institute of Technology, BiT
|  |  | Project: |  | Study on Productivity Norm of Water Construction Trades
|  |  | Consultant: |  | Faculty of Civil and Water Resource Engineering
|  |  | Lead Consultant: |  | Addis Ababa Institute of Technology, AAIT
|  |  | Client: |  | FDRE Construction Management Institute (CMI)
|  |  | Title of form: |  | Work Sampling
Data Collection Form Description |  |  | Observation Time (Hr.) |  | 2:00:00 ጥዋት - 3:00 ጥዋት | [17 empty] | 3:00:00 ጥዋት - 4:00 ጥዋት
Data count: | 35 | 09/ 05/2017 E.C | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Project Code: | 2 |  | Observation Time: (min) |  | 3 | 6 | 10 | 13 | 16 | 19 | 23 | 25 | 28 | 32 | 35 | 38 | 41 | 43 | 46 | 49 | 51 | 54 | 57 | 0 | 3 | 7 | 10 | 13 | 17 | 20 | 23 | 26 | 29 | 32 | 35 | 38 | 42 | 45 | 48 | 52
Crew tag: |  |  | CREW 1 | Direct | 4 | 3 | 4 | 5 | 4 | 6 | 2 | 5 | 4 | 4 | 3 | 6 | 5 | 5 | 5 | 4 | 3 | 4 | 3 | 2 | 5 | 4 | 2 | 4 | 2 | 5 | 6 | 4 | 6 | 5 | 3 | 4 | 5 | 4 | 6 | 6
Location: | Ground |  |  | Preparatory work | 2:00:00 ጥዋት - 3:00 ጥዋት 7: 3
|  |  |  | Tools and equipment | 3:00:00 ጥዋት - 4:00 ጥዋት 4: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 5: 2; 3:00:00 ጥዋት - 4:00 ጥዋት 7: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 10: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 12: 1
Task type code: | excavation |  |  | Material handling | 2:00:00 ጥዋት - 3:00 ጥዋት 2: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 3: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 9: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 10: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 11: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 13: 1; 2:00:00 ጥዋት - 3:00 ጥዋት 17: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 1: 2; 3:00:00 ጥዋት - 4:00 ጥዋት 7: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 8: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 13: 2; 3:00:00 ጥዋት - 4:00 ጥዋት 14: 1; 3:00:00 ጥዋት - 4:00 ጥዋት 15: 1
|  |  |  | Waiting | 1 | 2 |  |  | 2 |  |  | 1 | 1 |  | 2 |  |  | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 |  |  | 1 |  |  | 1 | 1 |  | 2
Travel | bar: 2:00:00 ጥዋት - 3:00 ጥዋት 1; 2:00:00 ጥዋት - 3:00 ጥዋት 4; 2:00:00 ጥዋት - 3:00 ጥዋት 7; 2:00:00 ጥዋት - 3:00 ጥዋት 10; 3:00:00 ጥዋት - 4:00 ጥዋት 2; 3:00:00 ጥዋት - 4:00 ጥዋት 5 to 3:00:00 ጥዋት - 4:00 ጥዋት 6
Personal | bar: 2:00:00 ጥዋት - 3:00 ጥዋት 3; 2:00:00 ጥዋት - 3:00 ጥዋት 17
|  |  |  | Sum | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Data Collector | Gedefaw | Dessie | Observation Time (Hr.) |  | 2:00:00 ጥዋት - 3:00 ጥዋት 1: 4:00:00 ጥዋት - 5:00 ጥዋት; 3:00:00 ጥዋት - 4:00 ጥዋት 1: 5:00:00 ጥዋት - 6:00 ጥዋት
|  |  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  |  | Observation Time: (min) |  | 55 | 59 | 3 | 7 | 10 | 13 | 17 | 20 | 23 | 26 | 29 | 32 | 35 | 39 | 42 | 45 | 48 | 52 | 55 | 59 | 3 | 7 | 11 | 14 | 17 | 20 | 23 | 26 | 29 | 32 | 36 | 40 | 43 | 47 | 50 | 53
|  |  | CREW 1 | Direct | 3 | 5 | 4 | 3 | 6 | 5 | 6 | 4 | 3 | 5 | 4 | 5 | 3 | 5 | 2 | 6 | 5 | 3 | 4 | 5 | 4 | 4 | 6 | 3 | 2 | 4 | 5 | 3 | 5 | 4 | 5 | 6 | 5 | 5 | 4 | 4
|  |  |  | Preparatory work | 4:00:00 ጥዋት - 5:00 ጥዋት 15: 3
|  |  |  | Tools and equipment | 4:00:00 ጥዋት - 5:00 ጥዋት 2: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 3: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 10: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 14: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 7: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 12: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 17: 1
|  |  |  | Material handling | 4:00:00 ጥዋት - 5:00 ጥዋት 1: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 4: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 8: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 11: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 13: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 18: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 2: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 3: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 6: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 9: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 10: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 13: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 15: 1
|  |  |  | Waiting | 4:00:00 ጥዋት - 5:00 ጥዋት 1: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 3: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 4: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 6: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 9: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 12: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 13: 2; 4:00:00 ጥዋት - 5:00 ጥዋት 17: 1; 4:00:00 ጥዋት - 5:00 ጥዋት 18: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 1: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 3: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 4: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 6: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 7: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 8: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 10: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 11: 2; 5:00:00 ጥዋት - 6:00 ጥዋት 16: 1; 5:00:00 ጥዋት - 6:00 ጥዋት 18: 2
Travel | bar: 4:00:00 ጥዋት - 5:00 ጥዋት 8; 4:00:00 ጥዋት - 5:00 ጥዋት 15; 5:00:00 ጥዋት - 6:00 ጥዋት 6; 5:00:00 ጥዋት - 6:00 ጥዋት 17
Personal | bar: 4:00:00 ጥዋት - 5:00 ጥዋት 9
|  |  |  | Sum | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6
|  |  | Observation Time (Hr.) |  | 4:00:00 ጥዋት - 5:00 ጥዋት 1: 7:00:00 - 8:00 ከሰዓት; 5:00:00 ጥዋት - 6:00 ጥዋት 1: 8:00:00 - 9:00 ከሰዓት
|  |  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  |  | Observation Time: (min) |  | 56 | 0 | 4 | 7 | 10 | 13 | 17 | 20 | 23 | 27 | 30 | 34 | 37 | 40 | 44 | 47 | 50 | 53 | 56 | 59 | 3 | 7 | 10 | 13 | 16 | 19 | 22 | 25 | 28 | 32 | 36 | 40 | 44 | 47 | 50 | 54
|  |  | CREW 1 | Direct | 3 | 4 | 4 | 5 | 4 | 6 | 6 | 3 | 5 | 5 | 6 | 2 | 5 | 2 | 5 | 2 | 4 | 4 | 5 | 3 | 5 | 4 | 6 | 5 | 5 | 4 | 5 | 3 | 4 | 4 | 6 | 5 | 3 | 4 | 5 | 5
|  |  |  | Preparatory work | 7:00:00 - 8:00 ከሰዓት 12: 3
|  |  |  | Tools and equipment | 7:00:00 - 8:00 ከሰዓት 5: 1; 7:00:00 - 8:00 ከሰዓት 10: 1; 7:00:00 - 8:00 ከሰዓት 14: 1; 7:00:00 - 8:00 ከሰዓት 16: 1; 7:00:00 - 8:00 ከሰዓት 18: 1; 8:00:00 - 9:00 ከሰዓት 2: 2; 8:00:00 - 9:00 ከሰዓት 8: 1; 8:00:00 - 9:00 ከሰዓት 11: 1; 8:00:00 - 9:00 ከሰዓት 15: 2
|  |  |  | Material handling | 7:00:00 - 8:00 ከሰዓት 1: 1; 7:00:00 - 8:00 ከሰዓት 2: 1; 7:00:00 - 8:00 ከሰዓት 8: 2; 7:00:00 - 8:00 ከሰዓት 9: 1; 7:00:00 - 8:00 ከሰዓት 13: 1; 7:00:00 - 8:00 ከሰዓት 16: 2; 7:00:00 - 8:00 ከሰዓት 17: 1; 8:00:00 - 9:00 ከሰዓት 1: 1; 8:00:00 - 9:00 ከሰዓት 4: 2; 8:00:00 - 9:00 ከሰዓት 6: 1; 8:00:00 - 9:00 ከሰዓት 10: 1; 8:00:00 - 9:00 ከሰዓት 14: 1; 8:00:00 - 9:00 ከሰዓት 16: 2; 8:00:00 - 9:00 ከሰዓት 17: 1
|  |  |  | Waiting | 7:00:00 - 8:00 ከሰዓት 1: 2; 7:00:00 - 8:00 ከሰዓት 3: 2; 7:00:00 - 8:00 ከሰዓት 4: 1; 7:00:00 - 8:00 ከሰዓት 8: 1; 7:00:00 - 8:00 ከሰዓት 12: 1; 7:00:00 - 8:00 ከሰዓት 14: 2; 7:00:00 - 8:00 ከሰዓት 15: 1; 7:00:00 - 8:00 ከሰዓት 16: 1; 7:00:00 - 8:00 ከሰዓት 17: 1; 8:00:00 - 9:00 ከሰዓት 2: 1; 8:00:00 - 9:00 ከሰዓት 3: 1; 8:00:00 - 9:00 ከሰዓት 7: 1; 8:00:00 - 9:00 ከሰዓት 9: 1; 8:00:00 - 9:00 ከሰዓት 11: 1; 8:00:00 - 9:00 ከሰዓት 12: 2; 8:00:00 - 9:00 ከሰዓት 15: 1; 8:00:00 - 9:00 ከሰዓት 18: 1
|  |  |  | Travel | 7:00:00 - 8:00 ከሰዓት 2: 1; 7:00:00 - 8:00 ከሰዓት 5: 1; 7:00:00 - 8:00 ከሰዓት 14: 1; 7:00:00 - 8:00 ከሰዓት 18: 1; 8:00:00 - 9:00 ከሰዓት 8: 1; 8:00:00 - 9:00 ከሰዓት 10: 2
Personal
|  |  |  | Sum | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
|  |  | Observation Time (Hr.) |  | 7:00:00 - 8:00 ከሰዓት 1: 9:00:00 -10:00 ከሰዓት; 8:00:00 - 9:00 ከሰዓት 1: 10:00:00 -11:00 ከሰዓት
|  |  | Observation Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  |  | Observation Time: (min) |  | 57 | 0 | 3 | 7 | 10 | 13 | 17 | 20 | 23 | 26 | 30 | 33 | 36 | 40 | 43 | 46 | 50 | 53 | 56 | 59 | 3 | 7 | 10 | 13 | 17 | 20 | 23 | 27 | 29
|  |  | CREW 1 | Direct | 3 | 2 | 5 | 4 | 5 | 4 | 4 | 2 | 4 | 3 | 4 | 5 | 4 | 6 | 2 | 4 | 6 | 5 | 4 | 5 | 5 | 4 | 4 |  | 3 | 5 | 6 | 2 | 1
|  |  |  | Preparatory work | 10:00:00 -11:00 ከሰዓት 6: 3
|  |  |  | Tools and equipment | 9:00:00 -10:00 ከሰዓት 1: 2; 9:00:00 -10:00 ከሰዓት 2: 2; 9:00:00 -10:00 ከሰዓት 6: 1; 9:00:00 -10:00 ከሰዓት 9: 1; 9:00:00 -10:00 ከሰዓት 10: 1; 9:00:00 -10:00 ከሰዓት 18: 1; 10:00:00 -11:00 ከሰዓት 2: 1; 10:00:00 -11:00 ከሰዓት 5: 1; 10:00:00 -11:00 ከሰዓት 7: 1; 10:00:00 -11:00 ከሰዓት 11: 1
|  |  |  | Material handling | 9:00:00 -10:00 ከሰዓት 2: 1; 9:00:00 -10:00 ከሰዓት 5: 1; 9:00:00 -10:00 ከሰዓት 8: 1; 9:00:00 -10:00 ከሰዓት 11: 1; 9:00:00 -10:00 ከሰዓት 12: 1; 9:00:00 -10:00 ከሰዓት 15: 2; 9:00:00 -10:00 ከሰዓት 16: 1; 10:00:00 -11:00 ከሰዓት 1: 2; 10:00:00 -11:00 ከሰዓት 5: 1; 10:00:00 -11:00 ከሰዓት 6: 1; 10:00:00 -11:00 ከሰዓት 8: 1; 10:00:00 -11:00 ከሰዓት 10: 2
|  |  |  | Waiting | 9:00:00 -10:00 ከሰዓት 1: 1; 9:00:00 -10:00 ከሰዓት 2: 1; 9:00:00 -10:00 ከሰዓት 3: 1; 9:00:00 -10:00 ከሰዓት 4: 2; 9:00:00 -10:00 ከሰዓት 7: 2; 9:00:00 -10:00 ከሰዓት 10: 2; 9:00:00 -10:00 ከሰዓት 11: 1; 9:00:00 -10:00 ከሰዓት 13: 2; 9:00:00 -10:00 ከሰዓት 15: 1; 9:00:00 -10:00 ከሰዓት 16: 1; 10:00:00 -11:00 ከሰዓት 3: 1; 10:00:00 -11:00 ከሰዓት 4: 2; 10:00:00 -11:00 ከሰዓት 6: 1; 10:00:00 -11:00 ከሰዓት 7: 2; 10:00:00 -11:00 ከሰዓት 10: 1; 10:00:00 -11:00 ከሰዓት 11: 1
|  |  |  | Travel | 9:00:00 -10:00 ከሰዓት 6: 1; 9:00:00 -10:00 ከሰዓት 8: 2; 9:00:00 -10:00 ከሰዓት 15: 1; 10:00:00 -11:00 ከሰዓት 6: 1; 10:00:00 -11:00 ከሰዓት 11: 3
Personal | bar: 9:00:00 -10:00 ከሰዓት 8; 10:00:00 -11:00 ከሰዓት 10
|  |  |  | Sum | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form -6 - Daily Input Variables
Project Code |  | 2 | Task/particular | excavation
Data Collector |  | Gedefaw Dessie | Data Count | 35 |  | Date | 09/05/2017 EC
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | observation | 6 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | observation | 1 foreman , 5 worker | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | observation | 1 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 5 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 4 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 5 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | interview | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | interview | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | interview | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | interview | 3 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | interview | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | interview | 2 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 5 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 10 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) |  |  | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) |  |  | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) |  |  | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) |  |  | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 34% | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).